## Epics & User Stories
Epic | User Story ID | User Story | Acceptance Criteria | Priority | Story Points | Status
Purchase Tickets & Seat Selection | US1.1 | As a user, I want to browse upcoming events so that I can find one to attend. | Events are displayed by category and date; User can view event details; Filtering works correctly. | Must Have | 3 | To Do
| US1.2 | As a user, I want to select my seats from a venue map so that I can choose my preferred location. | Venue map is interactive; Seats show availability; Selected seats are locked during checkout. | Must Have | 5 | To Do
| US1.3 | As a user, I want to pay securely for my tickets so that I can complete my purchase with confidence. | Payment processed via secure gateway; Confirmation email is sent; Ticket status updated to 'Purchased'. | Must Have | 8 | To Do
| US1.4 | As a user, I want to view an order summary before purchase so that I can verify my details. | Summary includes event name, seat numbers, total price, and payment method; User can confirm or edit. | Should Have | 2 | To Do
EP2 – Manage My Tickets | US2.1 | As a user, I want to view all my purchased tickets so that I can see upcoming events. | Tickets display event info, date, and QR code; Accessible via 'My Tickets' page. | Must Have | 3 | To Do
| US2.2 | As a user, I want to download my ticket as a PDF so that I can access it offline. | Download button functions correctly; File contains ticket details and QR code. | Should Have | 2 | To Do
| US2.3 | As a user, I want to transfer a ticket to another person so that they can attend in my place. | User can input recipient’s email; Recipient receives confirmation; Ticket status updated to 'Transferred'. | Could Have | 5 | To Do
EP3 – User Authentication & Profile | US3.1 | As a user, I want to create an account so that I can securely store my tickets. | Sign-up form includes email and password; Email verification sent; Account created successfully. | Must Have | 3 | To Do
| US3.2 | As a user, I want to log in so that I can access my tickets and personal info. | Login verifies credentials; Incorrect password gives error; Redirect to dashboard after success. | Must Have | 3 | To Do
| US3.3 | As a user, I want to update my profile details so that my information stays current. | Profile updates save to database; Changes reflected immediately; Validation on email/phone. | Should Have | 2 | To Do

## Personas
Persona | Role | Goals | Pain Points
Alex Johnson | Concerned Event Goer | Find reliable tickets easily; Ensure event entry; Stay updated on changes. | Confusing websites; Hidden fees; Lack of trust in ticket authenticity.
Jamie Lee | Sports Fan | Buy seats close to the action; Share experiences with friends; Manage season tickets. | Limited seat availability; Overpriced resales; Hard to transfer tickets.
Taylor Smith | Parent/Family User | Purchase multiple tickets quickly; Keep family tickets together; Ensure safe checkout. | Complex booking steps; Hard to track group tickets; Payment security concerns.

## Product Backlog
Story ID | Story Summary | Priority (MoSCoW) | Sprint Target | Notes
US1.1 | As a user, I want to browse upcoming events so that I can find one to attend. | Must Have | Sprint 1
US1.2 | As a user, I want to select my seats from a venue map so that I can choose my preferred location. | Must Have | Sprint 1
US1.3 | As a user, I want to pay securely for my tickets so that I can complete my purchase with confidence. | Must Have | Sprint 1
US1.4 | As a user, I want to view an order summary before purchase so that I can verify my details. | Should Have | Sprint 1
US2.1 | As a user, I want to view all my purchased tickets so that I can see upcoming events. | Must Have | Sprint 2
US2.2 | As a user, I want to download my ticket as a PDF so that I can access it offline. | Should Have | Sprint 2
US2.3 | As a user, I want to transfer a ticket to another person so that they can attend in my place. | Could Have | Sprint 2
US3.1 | As a user, I want to create an account so that I can securely store my tickets. | Must Have | Sprint 2
US3.2 | As a user, I want to log in so that I can access my tickets and personal info. | Must Have | Sprint 2
US3.3 | As a user, I want to update my profile details so that my information stays current. | Should Have | Sprint 2

## Estimation Log
Story ID | Team Members | Estimated Story Points | Discussion Notes
US1.1 | Conor McEvoy, Senan Morrissey | 3 | Consensus via Planning Poker.
US1.2 | Conor McEvoy, Senan Morrissey | 5 | Consensus via Planning Poker.
US1.3 | Conor McEvoy, Senan Morrissey | 8 | Consensus via Planning Poker.
US1.4 | Conor McEvoy, Senan Morrissey | 2 | Consensus via Planning Poker.
US2.1 | Conor McEvoy, Senan Morrissey | 3 | Consensus via Planning Poker.
US2.2 | Conor McEvoy, Senan Morrissey | 2 | Consensus via Planning Poker.
US2.3 | Conor McEvoy, Senan Morrissey | 5 | Consensus via Planning Poker.
US3.1 | Conor McEvoy, Senan Morrissey | 3 | Consensus via Planning Poker.
US3.2 | Conor McEvoy, Senan Morrissey | 3 | Consensus via Planning Poker.
US3.3 | Conor McEvoy, Senan Morrissey | 2 | Consensus via Planning Poker.

## Architecture & Design
Section | Description
Architecture Rationale | Ticket Expert will be a web app using React (frontend) and Node.js + Express (backend) with a PostgreSQL database. This stack supports scalability and team familiarity. Authentication uses JWT. Stripe is used for payments. Non-functional priorities: security, responsiveness, and user experience.
Key Risks & Mitigations | Risk: Payment failure – handled via retry and confirmation APIs. Risk: Data loss – mitigated via daily backups. Risk: Unauthorized access – mitigated with hashed passwords and role-based authentication.
UML Overview (Concept) | Actors: User, System. Use Cases: Browse Events, Select Seats, Purchase Ticket, View Tickets, Login. Primary entities: User, Event, Venue, Ticket, Payment.
Tiny Traceability Summary | EP1–Seat Selection ↔ SeatMapComponent; EP2–View Tickets ↔ TicketController; EP3–Login ↔ AuthService. All have related test cases referencing acceptance criteria.